## Gantt Chart
WBS NUMBER | TASK TITLE | START DATE | DATE COMPLETED | DURATION | April |  |  | May |  |  |  | June |  |  |  |  | July |  |  | August |  |  |  |  | September |  |  |  | October
[5 empty] | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5
1 | DESIGN PHASE
1.1 | Project Delegation | 2025-04-12 | 2025-04-14 | 2
1.2 | FlowChart | 2025-04-14 | 2025-04-22 | 8
2 | PROCUREMENT
2.1 | Tools to use | 2025-04-16 | 2025-07-20 | 4
2.2 | API to use | 2025-04-16 | 2025-04-23 | 7
3 | DEVELOPMENT
3.1 | Backend Coding | 2025-04-25 | 2025-06-27 | 63
3.2 | Connecting API | 2025-05-14 | 2025-05-20 | 6
3.2.1 | Monitoring | 2025-06-20 | 2025-07-01 | 11
3.3 | Debugging | 2025-04-30 | 2025-07-01 | 62
4 | TESTING
4.1 | API Testing | 2025-05-20 | 2025-05-31 | 11
4.2 | Quality Testing | 2025-07-01 | 2025-07-10 | 9
5 | LAUNCH
4.1 | Sample Project launch | 2025-07-10 |  | 0
4.2 | Final Project launch | 2025-10-30 | 2025-10-30 | 0
6 | EVALUATION
6.1 | Sir. Jay-al Evaluation | 2025-05-31 | 2025-06-08 | 8
6.2 | Final Defense | 2025-10-17 | 2025-10-17 | 0
7 | Updates/Modification
7.1 | Migrate Sql to MySql | 2025-08-01 | 2025-10-10 | 70
7.2 | Change Seeder Information | 2025-08-01 | 2025-08-31 | 30